## high burn rate
MB START | po | buyer | mb_end | description | vendor | mb_$_limit | mb_$_spent | division | options_remaining | option_(y/n) | comments | spending_comments | fiscal_year | duration_months | months_left | months_passed | pct_spent | desired_burn_rate | burn_rate | burn_status | projected_limit_date | watch_list_75%_spent
2014-06-25 | P527798 | MVASAVAD | 2019-06-24 | Central Chilled Water Systems Service -J F Fischer, Inc. | J.F. Fischer, Inc. | 1000000 | 883217.99 | Facilities | 1 two-yr option | Options |  |  | 2014 | 60 | 10 | 50 | 88.3218 | 1.6667 | 1.7664 | high | 2019-02-25 | watch
2016-04-11 | P535053 | DMACER | 2019-06-30 | Installation of Alarm & Fire Systems | Protection 1 | 306504.58 | 227287.87 | Facilities | No options | No options |  |  | 2016 | 39 | 11 | 28 | 74.1548 | 2.5641 | 2.6484 | high | 2019-05-11 | safe
2016-10-01 | P536960 | DMACER | 2019-09-30 | Locksmith Services First Call | Homeland Security Group dba Easter's Lock and Access | 200000 | 179510.83 | Facilities | No options | No options |  | requesting 300k | 2017 | 36 | 14 | 22 | 89.7554 | 2.7778 | 4.0798 | high | 2018-10-01 | watch
2016-10-01 | P536961 | DMACER | 2019-09-30 | Locksmith Services Second Call | BALTIMORE LOCK & HARDWARE, INC. | 149000 | 93587.34 | Facilities | 3 one year options | Options |  |  | 2017 | 36 | 14 | 22 | 62.8103 | 2.7778 | 2.855 | high | 2019-09-01 | safe
2017-01-01 | P537436 | MVASAVAD | 2019-12-31 | Drain Cleaning Service | Joseph Heil Company, Inc | 500000 | 332079.72 | Facilities | two one-yr renewals | Options |  |  | 2017 | 36 | 17 | 19 | 66.4159 | 2.7778 | 3.4956 | high | 2019-05-01 | safe
2017-02-06 | P538420 | DFINNERTY | 2020-02-05 | Interior Renovations, Carpentry and Associated Trades | First Potomac Environmental Corp. | 250000 | 188312.4 | Facilities | two one-yr renewals | Options |  | waiting on a response from purchases. We wanted to add $4M. Emailed mukesh 11/28 | 2017 | 36 | 18 | 18 | 75.325 | 2.7778 | 4.1847 | high | 2019-01-06 | watch
2017-02-06 | P538421 | DFINNERTY | 2020-02-05 | Interior Renovations, Carpentry and Associated Trades | C&W CONSTRUCTION COMPANY | 1650000 | 1287062 | Facilities | two one-yr renewals | Options |  | waiting on a response from purchases. We wanted to add $4M. Emailed mukesh 11/28 | 2017 | 36 | 18 | 18 | 78.0038 | 2.7778 | 4.3335 | high | 2019-01-06 | watch
2016-07-07 | P536071 | ABBEY | 2021-04-11 | Archibus Mobile Application Licenses (GSA Schedule Contract) | DLT Solutions, LLC | 12616.47 | 12616.47 | Facilities | No options | No options | annual purchase |  | 2017 | 57 | 32 | 25 | 100 | 1.7544 | 4 | high | 2018-08-07 | watch
2016-04-11 | P536303 | ABBEY | 2021-04-11 | Archibus Web Central Licenses Renewal 9GSA Schedule Contract #GS-35F-267DA) | DLT Solutions, LLC | 43516.41 | 43516.41 | Facilities | No options | No options | annual purchase |  | 2016 | 60 | 32 | 28 | 100 | 1.6667 | 3.5714 | high | 2018-08-11 | watch
2013-08-30 | P525136 | ABBEY | 2021-08-29 | Energy Performance Contract - Phase II | Johnson Controls Inc. | 7560711.56 | 6926441.23 | Facilities | No options | No options | monthly payments |  | 2014 | 96 | 37 | 59 | 91.611 | 1.0417 | 1.5527 | high | 2018-12-30 | watch

## expire 90 days
MB START | po | buyer | mb_end | description | vendor | mb_$_limit | mb_$_spent | division | options_remaining | option_(y/n) | comments | spending_comments | fiscal_year | duration_months | months_left | months_passed | pct_spent | desired_burn_rate | burn_rate | burn_status | projected_limit_date | watch_list_75%_spent
2015-11-18 | P533698 | DFINNERTY | 2018-11-17 | On-call Repair and Maint Services for Electronic Fire Alarm Systems | Fireline Corporation | 400000 | 200441.46 | Facilities | 2 one year renewals | Options |  |  | 2016 | 36 | 3 | 33 | 50.1104 | 2.7778 | 1.5185 | medium | 2021-04-18 | safe
2016-04-21 | P535185 | DFINNERTY | 2018-11-17 | On-call repair and maintenance services for electronic fire alarm systems. | Protection 1 | 365000 | 51955.86 | Facilities | 2 one year renewals | Options |  |  | 2016 | 31 | 3 | 28 | 14.2345 | 3.2258 | 0.50837 | low | 2032-08-21 | safe
2013-09-01 | P524796 | MVASAVAD | 2018-08-31 | Elevator Maintenance Service | Kone Inc. | 4412590 | 3355050.65 | Facilities | No options | No options |  | No changes necessary. Awaiting update from Karl on contract performance status recommendation. | 2014 | 60 | 1 | 59 | 76.0336 | 1.6667 | 1.2887 | medium | 2020-02-01 | watch
2016-09-08 | P536726 | DFINNERTY | 2018-09-07 | Calcium Chloride Pellets- Furnish and Deliver | CommoditiesUSA, Inc. | 96080 | 31080 | Facilities | No options | No options | FM will get a quote by Friday |  | 2017 | 24 | 1 | 23 | 32.348 | 4.1667 | 1.4064 | medium | 2022-08-08 | safe
2017-09-20 | P540931 | DFINNERTY | 2018-09-19 | Courthouse East Annual Elevator PM Services August 1, 2017 thru July 31, 2018 | Stratos Elevator, Inc. | 24984 | 0 | Facilities | No options | No options |  |  | 2018 | 12 | 1 | 11 | 0 | 8.3333 | 0 | low | 2017-09-20 | safe
2015-09-23 | P532945 | DFINNERTY | 2018-09-22 | Repair and Installation Services for Building Glass | aspen building products, inc | 620036 | 431741.12 | Facilities | No options | No options |  |  | 2016 | 36 | 1 | 35 | 69.6316 | 2.7778 | 1.9895 | medium | 2019-11-23 | safe
2014-10-08 | P529221 | BOLUWASU | 2018-10-07 | On-call Roofing Services | Simpson of Maryland, Inc. | 50000 | 35915.53 | Facilities | 1 one year options | Options | Bolu Oluwasuji will renew |  | 2015 | 48 | 2 | 46 | 71.8311 | 2.0833 | 1.5615 | medium | 2020-02-08 | safe
2014-10-08 | P529222 | BOLUWASU | 2018-10-07 | On-call Roofing Services | CitiRoof Corp. | 50000 | 35956.8 | Facilities | 1 one year options | Options | Bolu Oluwasuji will renew |  | 2015 | 48 | 2 | 46 | 71.9136 | 2.0833 | 1.5633 | medium | 2020-01-08 | safe
2014-10-08 | P529224 | BOLUWASU | 2018-10-07 | On-call Roofing Services | Autumn Contracting, Inc. | 50000 | 21700.61 | Facilities | 1 one year options | Options | Bolu Oluwasuji will renew |  | 2015 | 48 | 2 | 46 | 43.4012 | 2.0833 | 0.9435 | medium | 2023-07-08 | safe
2016-11-02 | P537224 | DFINNERTY | 2018-11-01 | Landscaping Services | The Garrison Company | 80000 | 37088 | Facilities | 3 one year options | Options | renew |  | 2017 | 24 | 3 | 21 | 46.36 | 4.1667 | 2.2076 | medium | 2020-08-02 | safe

## expire 180 days
MB START | po | buyer | mb_end | description | vendor | mb_$_limit | mb_$_spent | division | options_remaining | option_(y/n) | comments | spending_comments | fiscal_year | duration_months | months_left | months_passed | pct_spent | desired_burn_rate | burn_rate | burn_status | projected_limit_date | watch_list_75%_spent
2015-11-18 | P533698 | DFINNERTY | 2018-11-17 | On-call Repair and Maint Services for Electronic Fire Alarm Systems | Fireline Corporation | 400000 | 200441.46 | Facilities | 2 one year renewals | Options |  |  | 2016 | 36 | 3 | 33 | 50.1104 | 2.7778 | 1.5185 | medium | 2021-04-18 | safe
2016-04-21 | P535185 | DFINNERTY | 2018-11-17 | On-call repair and maintenance services for electronic fire alarm systems. | Protection 1 | 365000 | 51955.86 | Facilities | 2 one year renewals | Options |  |  | 2016 | 31 | 3 | 28 | 14.2345 | 3.2258 | 0.50837 | low | 2032-08-21 | safe
2013-09-01 | P524796 | MVASAVAD | 2018-08-31 | Elevator Maintenance Service | Kone Inc. | 4412590 | 3355050.65 | Facilities | No options | No options |  | No changes necessary. Awaiting update from Karl on contract performance status recommendation. | 2014 | 60 | 1 | 59 | 76.0336 | 1.6667 | 1.2887 | medium | 2020-02-01 | watch
2016-09-08 | P536726 | DFINNERTY | 2018-09-07 | Calcium Chloride Pellets- Furnish and Deliver | CommoditiesUSA, Inc. | 96080 | 31080 | Facilities | No options | No options | FM will get a quote by Friday |  | 2017 | 24 | 1 | 23 | 32.348 | 4.1667 | 1.4064 | medium | 2022-08-08 | safe
2017-09-20 | P540931 | DFINNERTY | 2018-09-19 | Courthouse East Annual Elevator PM Services August 1, 2017 thru July 31, 2018 | Stratos Elevator, Inc. | 24984 | 0 | Facilities | No options | No options |  |  | 2018 | 12 | 1 | 11 | 0 | 8.3333 | 0 | low | 2017-09-20 | safe
2015-09-23 | P532945 | DFINNERTY | 2018-09-22 | Repair and Installation Services for Building Glass | aspen building products, inc | 620036 | 431741.12 | Facilities | No options | No options |  |  | 2016 | 36 | 1 | 35 | 69.6316 | 2.7778 | 1.9895 | medium | 2019-11-23 | safe
2014-10-08 | P529221 | BOLUWASU | 2018-10-07 | On-call Roofing Services | Simpson of Maryland, Inc. | 50000 | 35915.53 | Facilities | 1 one year options | Options | Bolu Oluwasuji will renew |  | 2015 | 48 | 2 | 46 | 71.8311 | 2.0833 | 1.5615 | medium | 2020-02-08 | safe
2014-10-08 | P529222 | BOLUWASU | 2018-10-07 | On-call Roofing Services | CitiRoof Corp. | 50000 | 35956.8 | Facilities | 1 one year options | Options | Bolu Oluwasuji will renew |  | 2015 | 48 | 2 | 46 | 71.9136 | 2.0833 | 1.5633 | medium | 2020-01-08 | safe
2014-10-08 | P529224 | BOLUWASU | 2018-10-07 | On-call Roofing Services | Autumn Contracting, Inc. | 50000 | 21700.61 | Facilities | 1 one year options | Options | Bolu Oluwasuji will renew |  | 2015 | 48 | 2 | 46 | 43.4012 | 2.0833 | 0.9435 | medium | 2023-07-08 | safe
2016-11-02 | P537224 | DFINNERTY | 2018-11-01 | Landscaping Services | The Garrison Company | 80000 | 37088 | Facilities | 3 one year options | Options | renew |  | 2017 | 24 | 3 | 21 | 46.36 | 4.1667 | 2.2076 | medium | 2020-08-02 | safe
2015-12-01 | P533605 | PGOUGH | 2018-11-30 | Supply and Deliver Lumber to Various City Agencies | Pikesville Lumber Company | 860000 | 578110.1 | Facilities | No options | No options | Handled by buyer |  | 2016 | 36 | 4 | 32 | 67.2221 | 2.7778 | 2.1007 | medium | 2019-11-01 | safe
2015-12-16 | P534049 | DFINNERTY | 2018-12-15 | Furnish and Install Carpet and Various Floor Coverings | J.D. Carpets Inc. | 1800000 | 1032857.6 | Facilities | two one-year renewals | Options |  |  | 2016 | 36 | 4 | 32 | 57.381 | 2.7778 | 1.7932 | medium | 2020-07-16 | safe
2015-12-23 | P534098 | DFINNERTY | 2018-12-22 | Repairs & Maintenance Services for Automatic Sprinkler Systems | National Fire Protection, LLC | 75000 | 17933 | Facilities | No options | No options |  |  | 2016 | 36 | 4 | 32 | 23.9107 | 2.7778 | 0.74721 | low | 2027-01-23 | safe
2015-12-23 | P534097 | DFINNERTY | 2018-12-22 | Repairs & Maintenance Services for Automatic Sprinkler Systems | Fireline Corporation | 625000 | 249804.02 | Facilities | two one-year renewal options | Options |  |  | 2016 | 36 | 4 | 32 | 39.9686 | 2.7778 | 1.249 | medium | 2022-08-23 | safe
2014-01-25 | P526022 | MVASAVAD | 2019-01-24 | Maintenance &Repair Services for H.V.A.C.R | J.F. Fischer, Inc. | 9000000 | 5795484.44 | Facilities | No options | No options | working on renewal option; mukesh |  | 2014 | 60 | 5 | 54 | 64.3943 | 1.6667 | 1.1925 | medium | 2020-12-25 | safe
2014-01-25 | P526021 | MVASAVAD | 2019-01-24 | Maintenance &Repair Services for H.V.A.C.R-Denver-Elek | Denver-Elek | 1000000 | 257885.35 | Facilities | No options | No options | S Stricklin Having discussion with Purchasing to terminate service; purchases working on renewal option |  | 2014 | 60 | 5 | 54 | 25.7885 | 1.6667 | 0.47757 | low | 2031-06-25 | safe
2014-01-25 | P526023 | MVASAVAD | 2019-01-24 | Maintenance &Repair Services for H.V.A.C.R-Fresh Air company | fresh air company inc. | 2000000 | 991656.79 | Facilities | No options | No options | Purchases working on renewal option |  | 2014 | 60 | 5 | 54 | 49.5828 | 1.6667 | 0.9182 | medium | 2023-01-25 | safe
2014-01-29 | P526184 | MVASAVAD | 2019-01-28 | Maitenance and Repair Services- Plumbing and Heating-J.F. Fischer, Inc. | J.F. Fischer, Inc. | 6500000 | 5655960.07 | Facilities | 1 one-year renewal option | Options |  | Requested $2.3 million. Awaiting update on increase. | 2014 | 60 | 6 | 54 | 87.0148 | 1.6667 | 1.6114 | medium | 2019-03-29 | watch
2014-01-29 | P526182 | MVASAVAD | 2019-01-28 | Maitenance and Repair Services- Plumbing and Heating-Denver-Elek | Denver-Elek | 500000 | 365842.61 | Facilities | 1 two-yr option | Options | S Stricklin Having discussion with Purchasing to terminate service? |  | 2014 | 60 | 6 | 54 | 73.1685 | 1.6667 | 1.355 | medium | 2020-02-29 | safe
2014-01-29 | P526183 | MVASAVAD | 2019-01-28 | Maitenance and Repair Services- Plumbing and Heating-R.F.Warder,inc | R.F.Warder,inc | 2000000 | 1722849.85 | Facilities | 1 one-year renewal option | Options |  | Requested $600k. Awaiting update on increase. | 2014 | 60 | 6 | 54 | 86.1425 | 1.6667 | 1.5952 | medium | 2019-03-29 | watch
2016-02-01 | P534247 | MVASAVAD | 2019-01-31 | Hazardous Material Abatement Services | C&W CONSTRUCTION COMPANY | 2203333 | 1403062.59 | Facilities | No options | No options |  |  | 2016 | 36 | 6 | 30 | 63.6791 | 2.7778 | 2.1226 | medium | 2020-01-01 | safe
2016-02-01 | P534246 | MVASAVAD | 2019-01-31 | Hazardous Material Abatement Services | Retro Environmental, Inc. | 433333 | 243551 | Facilities | 2 one-year renewal options | Options |  |  | 2016 | 36 | 6 | 30 | 56.2041 | 2.7778 | 1.8735 | medium | 2020-07-01 | safe
2016-01-01 | P534248 | MVASAVAD | 2019-01-31 | Hazardous Material Abatement Services | Allec LLC | 463333 | 330028.05 | Facilities | two, one-year renewal options | Options |  |  | 2016 | 37 | 6 | 31 | 71.2291 | 2.7027 | 2.2977 | medium | 2019-08-01 | safe