## high burn rate
MB START | po | buyer | mb_end | description | vendor | mb_$_limit | mb_$_spent | division | options_remaining | option_(y/n) | comments | spending_comments | fiscal_year | duration_months | months_left | months_passed | pct_spent | desired_burn_rate | burn_rate | burn_status | projected_limit_date | watch_list_75%_spent
2017-09-13 | P540979 | SFELDMAN | 2018-09-12 | MLFY17T10-Load Packers-Solid Waste | Baltimore Mack Trucks, Inc. | 834824 | 834824 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 100 | 8.3333 | 9.0909 | high | 2018-08-13 | watch
2017-09-13 | P540980 | SFELDMAN | 2018-09-12 | MLFY17T10-Load Packers-Solid Waste | Maryland Industrial Trucks | 846125 | 846125 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 100 | 8.3333 | 9.0909 | high | 2018-08-13 | watch
2017-03-22 | P539270 | SFELDMAN | 2018-09-30 | MLFY17T6 - MEDICS | FESCO Emergency Sales | 1782624 | 1782624 | Fleet | No options | No options | Master Lease Purchase |  | 2017 | 18 | 2 | 17 | 100 | 5.5556 | 5.8824 | high | 2018-08-22 | watch
2016-12-21 | P538038 | KTREAT | 2019-12-20 | OEM and Aftermarket Parts and Repair for Lawn Mowers and Landscape Equipment | Port City Equipment Co | 20000 | 19691.84 | Fleet | two (2) one-year renewal options | Options |  |  | 2017 | 36 | 16 | 20 | 98.4592 | 2.7778 | 4.923 | high | 2018-08-21 | watch
2017-03-31 | P539028 | KTREAT | 2020-03-30 | O.E.M. Parts and Service for Wirtgen Cold Milling Machine | elliott & Frantz | 24500 | 11741.59 | Fleet | (3) three years with (2) two (1) one year renewal options | Options |  |  | 2017 | 36 | 20 | 16 | 47.9249 | 2.7778 | 2.9953 | high | 2019-12-31 | safe

## expire 90 days
MB START | po | buyer | mb_end | description | vendor | mb_$_limit | mb_$_spent | division | options_remaining | option_(y/n) | comments | spending_comments | fiscal_year | duration_months | months_left | months_passed | pct_spent | desired_burn_rate | burn_rate | burn_status | projected_limit_date | watch_list_75%_spent
2015-12-01 | P534308 | SFELDMAN | 2018-08-31 | OEM Parts & Service for Seagrave Fire Apparatus | Middleton & Meads | 416974.74 | 307903.81 | Fleet | one-one yr renewal | Options | Stuart Feldman will renew |  | 2016 | 33 | 1 | 32 | 73.8423 | 3.0303 | 2.3076 | medium | 2019-07-01 | safe
2015-09-01 | P532330 | BOLUWASU | 2018-08-31 | Gasoline And Diesel Fuel | PAPCO, Inc. | 4000000 | 652915.04 | Fleet | two one-year renewals | Options |  |  | 2016 | 36 | 1 | 35 | 16.3229 | 2.7778 | 0.46637 | low | 2033-07-01 | safe
2013-09-03 | P525152 | KTREAT | 2018-09-02 | OEM Parts and Service for Horton Medics | FESCO Emergency Sales | 800000 | 649885.42 | Fleet | No options | No options |  |  | 2014 | 60 | 1 | 59 | 81.2357 | 1.6667 | 1.3769 | medium | 2019-09-03 | watch
2014-09-11 | P528788 | BCOLE | 2018-09-10 | OEM Parts and Service for Hustler Lawn Equipment | GAMBRILLS EQUIPMENT CO.,INC. | 20000 | 155.7 | Fleet | one-one yr renewal | Options | Karen Addams will renew |  | 2015 | 48 | 1 | 47 | 0.7785 | 2.0833 | 0.016564 | low | 225640 | safe
2017-09-12 | P540427 | SFELDMAN | 2018-09-11 | Snow Emergency Food For Fleet Management Division | Prima Foods | 4990 | 0 | Fleet | one one-year renewal option | Options |  |  | 2018 | 12 | 1 | 11 | 0 | 8.3333 | 0 | low | 2017-09-12 | safe
2017-09-13 | P540978 | SFELDMAN | 2018-09-12 | MLFY17T6-Cutaway Vans w/Dry Freight Bodies | Century Ford of Mt. Airy Inc. | 955310 | 0 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 0 | 8.3333 | 0 | low | 2017-09-13 | safe
2017-09-13 | P540979 | SFELDMAN | 2018-09-12 | MLFY17T10-Load Packers-Solid Waste | Baltimore Mack Trucks, Inc. | 834824 | 834824 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 100 | 8.3333 | 9.0909 | high | 2018-08-13 | watch
2017-09-13 | P540980 | SFELDMAN | 2018-09-12 | MLFY17T10-Load Packers-Solid Waste | Maryland Industrial Trucks | 846125 | 846125 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 100 | 8.3333 | 9.0909 | high | 2018-08-13 | watch
2013-10-01 | P525025 | SZIEGLER | 2018-09-30 | Tires for Cars, Trucks & Heavy Equipment | Donald B. Rice Tire Co. | 3425000 | 2614879.64 | Fleet | No options | No options | On Hold by CPA |  | 2014 | 60 | 2 | 58 | 76.3469 | 1.6667 | 1.3163 | medium | 2020-01-01 | watch
2013-10-01 | P525024 | SZIEGLER | 2018-09-30 | Tires for Cars, Trucks & Heavy Equipment | Admiral Tire | 4826000 | 2811665.39 | Fleet | No options | No options | ON Hold by CPA |  | 2014 | 60 | 2 | 58 | 58.2608 | 1.6667 | 1.0045 | medium | 2022-01-01 | safe
2013-10-01 | P524844 | KTREAT | 2018-09-30 | BG Chemicals | CROVATO PRODUCTS AND SERVICES, LLC | 560000 | 387058.69 | Fleet | No options | No options |  |  | 2014 | 60 | 2 | 58 | 69.1176 | 1.6667 | 1.1917 | medium | 2020-09-01 | safe
2013-10-01 | P526537 | KTREAT | 2018-09-30 | OEM Parts - EJ Ward Canceivers | E.J. Ward, Inc. | 500000 | 288400.47 | Fleet | one one-yr renewal | Options | Karen Addams will renew Change Order added $150,000.00 |  | 2014 | 60 | 2 | 58 | 57.6801 | 1.6667 | 0.99448 | medium | 2022-02-01 | safe
2015-10-01 | P532867 | KTREAT | 2018-09-30 | OEM Parts and Service for Onan and Cummins Generators | Cummins Power Systems LLC | 24000 | 12260.75 | Fleet | No options | No options | Karen Addams will renew |  | 2016 | 36 | 2 | 34 | 51.0865 | 2.7778 | 1.5025 | medium | 2021-04-01 | safe
2017-03-22 | P539270 | SFELDMAN | 2018-09-30 | MLFY17T6 - MEDICS | FESCO Emergency Sales | 1782624 | 1782624 | Fleet | No options | No options | Master Lease Purchase |  | 2017 | 18 | 2 | 17 | 100 | 5.5556 | 5.8824 | high | 2018-08-22 | watch
2014-10-08 | P529066 | KTREAT | 2018-10-07 | OEM Parts and Service for UD Cab & Chassis Trucks | Norris Chesapeake Truck Sales LLC | 910000 | 594267.99 | Fleet | 1, one-year renewal options | Options | Karen will renew Change Order in process for $110,000.00 |  | 2015 | 48 | 2 | 46 | 65.3042 | 2.0833 | 1.4197 | medium | 2020-08-08 | safe
2014-11-01 | P529191 | KTREAT | 2018-10-31 | OEM Parts and Service for Sterling Heavy Trucks | Norris Chesapeake Truck Sales LLC | 140100 | 67656.72 | Fleet | 1 one-yr option | Options |  |  | 2015 | 48 | 3 | 45 | 48.2917 | 2.0833 | 1.0731 | medium | 2022-08-01 | safe
2014-11-01 | P529190 | KTREAT | 2018-10-31 | OEM Parts and Service for Sterling Heavy Trucks | Waste Equipment Sales & Service, LLC | 159900 | 80914.58 | Fleet | No options | No options |  |  | 2015 | 48 | 3 | 45 | 50.6032 | 2.0833 | 1.1245 | medium | 2022-03-01 | safe
2011-11-01 | P518465 | SFELDMAN | 2018-10-31 | Maintenance, Parts and Repair Service for The Fire Boats | The General Ship Repair Corp. | 350000 | 0 | Fleet | 2 two-yr options | Options | Renewal/amt increase change order in process, anticipated BOE date 8/17/16; Went to Board 9142016; Kristy will update before end of month. |  | 2012 | 84 | 3 | 81 | 0 | 1.1905 | 0 | low | 2011-11-01 | safe
2011-11-01 | P518466 | SFELDMAN | 2018-10-31 | Maintenance, Parts and Repair Service for The Fire Boats | Marcon Engineering | 3650000 | 2798277.87 | Fleet | 2 two-yr options | Options | Renewal/amt increase change order in process, anticipated BOE date 8/17/16; Went to Board 9142016; Kristy will update before end of month. |  | 2012 | 84 | 3 | 81 | 76.6651 | 1.1905 | 0.94648 | medium | 2020-08-01 | watch
2015-11-01 | P533048 | KHAMMER2 | 2018-10-31 | Diesel Fuel for Generators | C.Hoffberger co | 300000 | 101059.43 | Fleet | two one-year renewal options | Options |  |  | 2016 | 36 | 3 | 33 | 33.6865 | 2.7778 | 1.0208 | medium | 2023-12-01 | safe
2017-11-11 | P541673 | KTREAT | 2018-11-10 | FASTER WEB Migration Upgrade | CCG Systems, Inc. | 373163 | 0 | Fleet | No options | No options | annual purchase |  | 2018 | 12 | 3 | 9 | 0 | 8.3333 | 0 | low | 2017-11-11 | safe

## expire 180 days
MB START | po | buyer | mb_end | description | vendor | mb_$_limit | mb_$_spent | division | options_remaining | option_(y/n) | comments | spending_comments | fiscal_year | duration_months | months_left | months_passed | pct_spent | desired_burn_rate | burn_rate | burn_status | projected_limit_date | watch_list_75%_spent
2017-01-11 | P538021 | KTREAT | 2019-01-10 | Parts and Service for All Terrain Vehicles and Dirt Bikes | GLEN BURNIE MOTORSPORTS | 15000 | 1635 | Fleet | 1 one-yr option | Options | This item has renewals. It will be started in December. |  | 2017 | 24 | 5 | 19 | 10.9 | 4.1667 | 0.57368 | low | 2031-07-11 | safe
2014-04-15 | P526059 | KTREAT | 2019-01-14 | OEM Parts for Billy Goat Lawn Mowers | BMR INC | 24000 | 2694.12 | Fleet | No options | No options | This item has a renewal. It will be started in December. |  | 2014 | 57 | 5 | 52 | 11.2255 | 1.7544 | 0.21588 | low | 2052-11-15 | safe
2015-12-01 | P534308 | SFELDMAN | 2018-08-31 | OEM Parts & Service for Seagrave Fire Apparatus | Middleton & Meads | 416974.74 | 307903.81 | Fleet | one-one yr renewal | Options | Stuart Feldman will renew |  | 2016 | 33 | 1 | 32 | 73.8423 | 3.0303 | 2.3076 | medium | 2019-07-01 | safe
2015-09-01 | P532330 | BOLUWASU | 2018-08-31 | Gasoline And Diesel Fuel | PAPCO, Inc. | 4000000 | 652915.04 | Fleet | two one-year renewals | Options |  |  | 2016 | 36 | 1 | 35 | 16.3229 | 2.7778 | 0.46637 | low | 2033-07-01 | safe
2013-09-03 | P525152 | KTREAT | 2018-09-02 | OEM Parts and Service for Horton Medics | FESCO Emergency Sales | 800000 | 649885.42 | Fleet | No options | No options |  |  | 2014 | 60 | 1 | 59 | 81.2357 | 1.6667 | 1.3769 | medium | 2019-09-03 | watch
2014-09-11 | P528788 | BCOLE | 2018-09-10 | OEM Parts and Service for Hustler Lawn Equipment | GAMBRILLS EQUIPMENT CO.,INC. | 20000 | 155.7 | Fleet | one-one yr renewal | Options | Karen Addams will renew |  | 2015 | 48 | 1 | 47 | 0.7785 | 2.0833 | 0.016564 | low | 225640 | safe
2017-09-12 | P540427 | SFELDMAN | 2018-09-11 | Snow Emergency Food For Fleet Management Division | Prima Foods | 4990 | 0 | Fleet | one one-year renewal option | Options |  |  | 2018 | 12 | 1 | 11 | 0 | 8.3333 | 0 | low | 2017-09-12 | safe
2017-09-13 | P540978 | SFELDMAN | 2018-09-12 | MLFY17T6-Cutaway Vans w/Dry Freight Bodies | Century Ford of Mt. Airy Inc. | 955310 | 0 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 0 | 8.3333 | 0 | low | 2017-09-13 | safe
2017-09-13 | P540979 | SFELDMAN | 2018-09-12 | MLFY17T10-Load Packers-Solid Waste | Baltimore Mack Trucks, Inc. | 834824 | 834824 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 100 | 8.3333 | 9.0909 | high | 2018-08-13 | watch
2017-09-13 | P540980 | SFELDMAN | 2018-09-12 | MLFY17T10-Load Packers-Solid Waste | Maryland Industrial Trucks | 846125 | 846125 | Fleet | No options | No options | Master Lease Purchase |  | 2018 | 12 | 1 | 11 | 100 | 8.3333 | 9.0909 | high | 2018-08-13 | watch
2013-10-01 | P525025 | SZIEGLER | 2018-09-30 | Tires for Cars, Trucks & Heavy Equipment | Donald B. Rice Tire Co. | 3425000 | 2614879.64 | Fleet | No options | No options | On Hold by CPA |  | 2014 | 60 | 2 | 58 | 76.3469 | 1.6667 | 1.3163 | medium | 2020-01-01 | watch
2013-10-01 | P525024 | SZIEGLER | 2018-09-30 | Tires for Cars, Trucks & Heavy Equipment | Admiral Tire | 4826000 | 2811665.39 | Fleet | No options | No options | ON Hold by CPA |  | 2014 | 60 | 2 | 58 | 58.2608 | 1.6667 | 1.0045 | medium | 2022-01-01 | safe
2013-10-01 | P524844 | KTREAT | 2018-09-30 | BG Chemicals | CROVATO PRODUCTS AND SERVICES, LLC | 560000 | 387058.69 | Fleet | No options | No options |  |  | 2014 | 60 | 2 | 58 | 69.1176 | 1.6667 | 1.1917 | medium | 2020-09-01 | safe
2013-10-01 | P526537 | KTREAT | 2018-09-30 | OEM Parts - EJ Ward Canceivers | E.J. Ward, Inc. | 500000 | 288400.47 | Fleet | one one-yr renewal | Options | Karen Addams will renew Change Order added $150,000.00 |  | 2014 | 60 | 2 | 58 | 57.6801 | 1.6667 | 0.99448 | medium | 2022-02-01 | safe
2015-10-01 | P532867 | KTREAT | 2018-09-30 | OEM Parts and Service for Onan and Cummins Generators | Cummins Power Systems LLC | 24000 | 12260.75 | Fleet | No options | No options | Karen Addams will renew |  | 2016 | 36 | 2 | 34 | 51.0865 | 2.7778 | 1.5025 | medium | 2021-04-01 | safe
2017-03-22 | P539270 | SFELDMAN | 2018-09-30 | MLFY17T6 - MEDICS | FESCO Emergency Sales | 1782624 | 1782624 | Fleet | No options | No options | Master Lease Purchase |  | 2017 | 18 | 2 | 17 | 100 | 5.5556 | 5.8824 | high | 2018-08-22 | watch
2014-10-08 | P529066 | KTREAT | 2018-10-07 | OEM Parts and Service for UD Cab & Chassis Trucks | Norris Chesapeake Truck Sales LLC | 910000 | 594267.99 | Fleet | 1, one-year renewal options | Options | Karen will renew Change Order in process for $110,000.00 |  | 2015 | 48 | 2 | 46 | 65.3042 | 2.0833 | 1.4197 | medium | 2020-08-08 | safe
2014-11-01 | P529191 | KTREAT | 2018-10-31 | OEM Parts and Service for Sterling Heavy Trucks | Norris Chesapeake Truck Sales LLC | 140100 | 67656.72 | Fleet | 1 one-yr option | Options |  |  | 2015 | 48 | 3 | 45 | 48.2917 | 2.0833 | 1.0731 | medium | 2022-08-01 | safe
2014-11-01 | P529190 | KTREAT | 2018-10-31 | OEM Parts and Service for Sterling Heavy Trucks | Waste Equipment Sales & Service, LLC | 159900 | 80914.58 | Fleet | No options | No options |  |  | 2015 | 48 | 3 | 45 | 50.6032 | 2.0833 | 1.1245 | medium | 2022-03-01 | safe
2011-11-01 | P518465 | SFELDMAN | 2018-10-31 | Maintenance, Parts and Repair Service for The Fire Boats | The General Ship Repair Corp. | 350000 | 0 | Fleet | 2 two-yr options | Options | Renewal/amt increase change order in process, anticipated BOE date 8/17/16; Went to Board 9142016; Kristy will update before end of month. |  | 2012 | 84 | 3 | 81 | 0 | 1.1905 | 0 | low | 2011-11-01 | safe
2011-11-01 | P518466 | SFELDMAN | 2018-10-31 | Maintenance, Parts and Repair Service for The Fire Boats | Marcon Engineering | 3650000 | 2798277.87 | Fleet | 2 two-yr options | Options | Renewal/amt increase change order in process, anticipated BOE date 8/17/16; Went to Board 9142016; Kristy will update before end of month. |  | 2012 | 84 | 3 | 81 | 76.6651 | 1.1905 | 0.94648 | medium | 2020-08-01 | watch
2015-11-01 | P533048 | KHAMMER2 | 2018-10-31 | Diesel Fuel for Generators | C.Hoffberger co | 300000 | 101059.43 | Fleet | two one-year renewal options | Options |  |  | 2016 | 36 | 3 | 33 | 33.6865 | 2.7778 | 1.0208 | medium | 2023-12-01 | safe
2010-08-01 | P514297 | KHAMMER2 | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | The Baltimore Auto Supply Company | 3782000 | 3538730.66 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 93.5677 | 1 | 0.97466 | medium | 2019-02-01 | watch
2010-08-01 | P514298 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | IEH Auto Parts LLC | 666000 | 610132.51 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 91.6115 | 1 | 0.95429 | medium | 2019-04-01 | watch
2010-08-01 | P514299 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | Quality Automotive Whse | 1899000 | 1505733.64 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 79.2909 | 1 | 0.82595 | medium | 2020-09-01 | watch
2010-08-01 | P514300 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | PA Southern LLC. | 35000 | 14717.26 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 42.0493 | 1 | 0.43801 | medium | 2029-08-01 | safe
2010-08-01 | P514301 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | FLEETPRIDE INC | 353000 | 249519.72 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 70.6855 | 1 | 0.73631 | medium | 2021-11-01 | safe
2010-08-01 | P514302 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | Salvo Limited Partnership, LLLP | 211000 | 126725.54 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 60.0595 | 1 | 0.62562 | medium | 2023-11-01 | safe
2010-08-01 | P514303 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | ROK Brothers Inc. | 700000 | 553321.33 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 79.0459 | 1 | 0.82339 | medium | 2020-09-01 | watch
2010-08-01 | P514304 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | Service Parts Company DBA Papa Auto Parts | 166000 | 136051.85 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 81.9589 | 1 | 0.85374 | medium | 2020-05-01 | watch
2010-08-01 | P514305 | KTREAT | 2018-11-30 | Aftermarket Parts and Supplies for Cars and Light Trucks | CRW Parts | 4000 | 895.37 | Fleet | No options | No options | this is web migration Agreement, it has gone to the Board. I am awaiting approval with ALL signatures. |  | 2011 | 100 | 4 | 96 | 22.3843 | 1 | 0.23317 | low | 2046-04-01 | safe
2013-12-01 | P526180 | KTREAT | 2018-11-30 | OEM Parts & Service for Altec Bucket Trucks | Altec Industries Inc | 300000 | 38846.64 | Fleet | 1 one-yr option | Options | Scheduled for the Board 10-18-17 |  | 2014 | 60 | 4 | 56 | 12.9489 | 1.6667 | 0.23123 | low | 2049-12-01 | safe
2014-12-01 | P528895 | KTREAT | 2018-11-30 | O.E.M Parts and Service For Peterbilt Heavy Truck | Peterbilt of Baltimore | 20000 | 1074.6 | Fleet | 1 one-yr option | Options | Scheduled for the Board 10-25-17 |  | 2015 | 48 | 4 | 44 | 5.373 | 2.0833 | 0.12211 | low | 2083-02-01 | safe
2014-12-01 | P528896 | KTREAT | 2018-11-30 | O.E.M Parts and Service For Peterbilt Heavy Truck | Columbia Fleet Service | 80000 | 23239.38 | Fleet | 1 one-yr option | Options | Scheduled for the Board 10-25-17 |  | 2015 | 48 | 4 | 44 | 29.0492 | 2.0833 | 0.66021 | low | 2027-07-01 | safe
2014-12-01 | P529415 | BCOLE | 2018-11-30 | OEM Parts and Service for Freightliner Trucks | BALTIMORE FREIGHTLINER | 2750000 | 1115614.22 | Fleet | 1 one-yr option | Options |  |  | 2015 | 48 | 4 | 44 | 40.5678 | 2.0833 | 0.922 | medium | 2023-12-01 | safe
2014-12-01 | P529416 | BCOLE | 2018-11-30 | OEM Parts and Service for Freightliner Trucks | Norris Chesapeake Truck Sales LLC | 250000 | 81122.65 | Fleet | 1 one-yr option | Options |  |  | 2015 | 48 | 4 | 44 | 32.4491 | 2.0833 | 0.73748 | medium | 2026-03-01 | safe
2014-12-01 | P529439 | KTREAT | 2018-11-30 | O.E.M Parts & Service for JCB & LeeBoy Equipment | Valley Supply and Equipment Co., Inc. | 425000 | 202756.93 | Fleet | 1 one-yr option | Options | Scheduled for the Board 10-18-17 |  | 2015 | 48 | 4 | 44 | 47.7075 | 2.0833 | 1.0843 | medium | 2022-08-01 | safe
2015-12-01 | P533675 | BCOLE | 2018-11-30 | Vehicle Glass Repair and Installation Services | Millenium 2, Inc. | 25000 | 1949.99 | Fleet | 2 one-year renewal options | Options |  |  | 2016 | 36 | 4 | 32 | 7.8 | 2.7778 | 0.24375 | low | 2050-02-01 | safe
2015-12-01 | P533676 | BCOLE | 2018-11-30 | Vehicle Glass Repair and Installation Services | Smith Auto Glass | 10000 | 0 | Fleet | 2 one-year renewal options | Options |  |  | 2016 | 36 | 4 | 32 | 0 | 2.7778 | 0 | low | 2015-12-01 | safe
2015-01-01 | P529506 | KTREAT | 2018-12-31 | Parts and Maintenance for Fuel Dispensing Equipment | Total Environmental Concepts, Inc. | 300000 | 188747.29 | Fleet | two one-year renewal options | Options |  |  | 2015 | 48 | 5 | 43 | 62.9158 | 2.0833 | 1.4632 | medium | 2020-09-01 | safe
2016-01-20 | P534281 | BCOLE | 2019-01-19 | Decals and Striping | Shannon-Baum Signs, Inc. | 20000 | 0 | Fleet | two one-year options | Options |  |  | 2016 | 36 | 5 | 31 | 0 | 2.7778 | 0 | low | 2016-01-20 | safe
2016-01-20 | P534307 | KTREAT | 2019-01-19 | OEM Parts and Service for Pierce Fire Apparatus | Atlantic Emergency Solutions, Inc. | 2500000 | 1411391.18 | Fleet | two-one year renewal options | Options |  |  | 2016 | 36 | 5 | 31 | 56.4556 | 2.7778 | 1.8211 | medium | 2020-07-20 | safe
2016-02-01 | P533925 | KTREAT | 2019-01-31 | Truck Accessories | Admiral Tire | 200000 | 47306.86 | Fleet | two one-year options | Options |  |  | 2016 | 36 | 6 | 30 | 23.6534 | 2.7778 | 0.78845 | low | 2026-08-01 | safe
2016-02-01 | P533956 | KTREAT | 2019-01-31 | OEM Parts and Service for FUSO Mitsubishi Trucks | Waste Equipment Sales & Service, LLC | 4000000 | 1709896.61 | Fleet | two-one year renewal options | Options |  |  | 2016 | 36 | 6 | 30 | 42.7474 | 2.7778 | 1.4249 | medium | 2021-12-01 | safe
2017-11-11 | P541673 | KTREAT | 2018-11-10 | FASTER WEB Migration Upgrade | CCG Systems, Inc. | 373163 | 0 | Fleet | No options | No options | annual purchase |  | 2018 | 12 | 3 | 9 | 0 | 8.3333 | 0 | low | 2017-11-11 | safe